## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-01-8h-8ball
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
Given that I am on the products page when there are products in the inventory then I see each product and short description.
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As a buyer I want to see all prepackaged tea/coffee options so I can choose the blend I like best | Given that I am on the product list page when I click on one of the options then I can see more information about it.
As a buyer I want to browse a list of products so that I can choose what to purchase | Given there are products in the inventory when I select to browse all products then I am taken to a list of all the products
As an owner I want to view a list of customer names, addresses, and orders so that I can fulfill shipments | Given an order has been placed when I check for orders then I should see all unfulfilled orders until I have designated them shipped
As a buyer I want to add my purchase to a single cart so I can have all my packages shipped to one location | Given I want to purchase a product when I click the add to cart button then I expect to have it saved to my cart
As an Owner I want to be able to remove products from the e-store so I can eliminate unpopular blends | Given a product exists when a product is deleted then the product will be removed from the site
As an Owner I want to be able to modify existing products in the e-store so I can update pricing and stock. | Given a product exists when a product is modified then the product should update in the system
As an Owner I want to be able to add new products to the e-store so I can expand the potential range of customers. | Given inventory exists when create a new product then the product will be tied to the inventory
As a Buyer I want to input my address so I can receive the contents of a cart in the mail. | Given that I am ready to have my order shipped when I enter my address then I expect to have it delivered sometime in the future
As an Owner I want to be able to add new Admins to the e-store so I can delegate who can access the inventory. | Given a user account has been created when I add that account to the list of admis then the user account will be able to manage inventory
As a Buyer I want to have my package covered in gift wrap so it can be shipped as a gift. | Given I have my package in the checkout when I select the gift option then I will be taken to choose wrapping
As a Buyer I want to add a custom picture to the packing so it can feel special and stand out. | Given I have selected the gift option when I upload my own photo then my photo will be applied to the packaging
As a Buyer I want to add a personalized card with my order so I can convey my intentions to the recipient. | Given I have a package in my checkout when I click the gift option then I will be directed to write a message
As a Buyer I want to see the option to make a custom blend so I can mix tea leaves or coffee grounds to create a personalized package. | Given that I want to create a custom blend when I click the custom blend option then I expect to be able to see the different ingredients I can blend together
As a Buyer I want to add my packages to multiple carts so I can have certain orders shipped to different locations. | Given I want to send packages to multiple addresses when I click the add to cart button then I expect to be given the option to select which cart to add to
As an Owner I want to be able to modify the privileges of an existing Admin in the e-store so I can control their capabilities. | Given an admin account exists when I change the permissions for that user then that user will have modified abilities within the store
As an Owner I want to be able to remove Admins from the e-store so I can decrease the workforce. | Given there exists another admin on the website when I remove them from the admin list then they no longer have admin rights